## Sheet1
Task | Duration | Weeks to Complete
Dataset Collection | 01 Nov - 08 Nov 2022 | 1 Week
Pre-Processsing | 08 Nov - 22 Nov 2022 | 2 Weeks
Image Segmentation | 22 Nov - 13 Dec 2022 | 3 Weeks
Feature Extraction | 13 Dec 2022 - 03 Jan 2023 | 3 Weeks
Data Labelling | 03 Jan - 09 Jan 2023 | 1 Week
Training Data | 09 Jan - 30 Jan 2023 | 3 Weeks
Testing Data | 30 Jan - 20 Feb 2023 | 3 Weeks
Report Writing | 20 Feb - 03 April 2023 | 6 Weeks
Interface | 03 April - 17 April 2023 | 2 Weeks