## Sheet1
Task | Start Date | Days to Complete
Dataset Collection | 2022-11-01 | 7
Pre-Processsing | 2022-11-08 | 14
Image Segmentation | 2022-11-22 | 21
Feature Extraction | 2022-12-13 | 21
Data Labelling | 2023-01-03 | 7
Training Data | 2023-01-10 | 21
Testing Data | 2023-01-31 | 21
Report Writing | 2023-02-21 | 42
Interface | 2023-04-04 | 14